## Instructions
OMB Control No. 0648-0384
Instructions | Expiration Date 01/31/2025
Please follow instructions below to fill out your milestone chart ("Milestone chart" tab). See example milestone charts under "Example" tabs.
For FFO-XXXX, the anticipated project start date is XXXX XX, XXXX. Please align your milestones and tasks in this Gantt chart using the start date proposed in your application
1. Fill out Columns A-E as follows (See "Example" tabs):
a. Each task (column B) should fit under a project milestone (in bold, column A). Please add additional milestones in column A as needed and add the associated tasks for each milestone in separate rows in column B.
b. Please provide a category of your choosing for each task in column C. Suggestions include (but are not limited to): Field Preparation, Field Work Sampling, Lab Analyses, Data Analyses, Data Management, Outreach, Reporting/Publications, Meetings. You may have different task categories under a single milestone (e.g., see milestone 2 in “Example” tab).
c. Please add the start date and completion date for each task in columns D and E, respectively.
Note: Although the template only contains 3 milestones with 3 tasks each, there is no limit to the number of milestones or tasks associated with each milestone.
2. Using the timeline provided in rows 1 through 3, please fill in the appropriate cells for each task using blue that corresponds to the start and completion date provided in columns D and E, respectively. Blue cells can be continuous (e.g., from 9/1/2021-1/31/2022) or on a frequency of your choosing (e.g., bi-monthly or quarterly meetings). Note - years are in fiscal years (FY2021, FY2022).
3. Using the timeline provided in rows 1 through 3, please fill in the appropriate cells for each milestone using green that corresponds to the start and completion date of all of the tasks associated with that milestone. Note - years are in federal fiscal years (FY2021, FY2022).
4. Please save the spreadsheet as "[PI Last Name- Project title keyword- milestone chart]" and submit the file along with your full application to Grants.gov ahead of the deadline for this funding opportunity

## Milestone Chart
Milestone | Task | Task Category | Task Start Date | Task Completion Date | 2021 | 2022
[6 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[5 empty] | S | O | N | D | J | F | M | A | M | J | J | A
Milestone 1: [Enter name of milestone] | bar: S to Q4 A
1.1 | [Enter first task] | [Enter category] | [Enter start date] | [Enter due date]
1.2 | [Enter second task] | [Enter category] | [Enter start date] | [Enter due date]
1.3 | [Enter third task] | [Enter category] | [Enter start date] | [Enter due date]
Milestone 2: [Enter name of milestone] | bar: S to Q4 A
2.1 | [Enter first task] | [Enter category] | [Enter start date] | [Enter due date]
2.2 | [Enter second task] | [Enter category] | [Enter start date] | [Enter due date]
2.3 | [Enter third task] | [Enter category] | [Enter start date] | [Enter due date]
Milestone 3: [Enter name of milestone] | bar: S to Q4 A
3.1 | [Enter first task] | [Enter category] | [Enter start date] | [Enter due date]
3.2 | [Enter second task] | [Enter category] | [Enter start date] | [Enter due date]
3.3 | [Enter third task] | [Enter category] | [Enter start date] | [Enter due date]
Etc.

## Example 1 (research project)
| Task | Task Category | Task Start Date | Task Completion Date | 2021 | [6 empty] | 2022 | [11 empty] | 2023
[5 empty] | Q3 | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3
[5 empty] | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
Milestone 1: Field Data | bar: Q3 J to Q4 S
1.1 | Expedition #1: Pre-Expedition Preparation | Cruise | 2017-06-01 | 2017-06-30 | bar: Q3 J
1.2 | Expedition #1: Full Depth Cruise | Cruise | 2017-07-01 | 2017-07-31 | bar: Q4 J
1.3 | Expedition #2: Pre-Expedition Preparation | Cruise | 2017-06-01 | 2017-07-31 | bar: Q3 J to Q4 J
1.4 | Expedition #2: Mesophotic Cruise 1 | Cruise | 2017-10-01 | 2017-10-31 | bar: Q1 O
1.5 | Expedition #3: Pre-Expedition Preparation | Cruise | 2018-02-01 | 2018-05-31 | bar: Q3 M; Q4 A
1.6 | Expedition #3: Mesophotic Cruise 2 | Cruise | 2018-06-01 | 2018-06-30 | bar: Q3 J; Q4 S
Milestone 2: Field Data Processing | bar: Q3 J to Q2 M
2.1 | Voucher specimens curation | Data Processing | 2017-08-01 | 2018-07-31 | bar: Q4 A to Q1 D; Q3 J to Q4 J; Q4 S to Q1 O
2.2 | DNA extractions | Data Processing | 2017-09-01 | 2018-07-31 | bar: Q4 S to Q2 F; Q4 J; Q1 O to Q1 N
2.3 | DNA barcoding | Data Processing | 2017-09-01 | 2018-09-30 | bar: Q4 S to Q1 N
2.4 | Publication of DNA barcoding data on GenBank | Data Management | 2018-01-01 | 2018-11-30 | bar: Q2 J to Q4 J; Q1 O to Q2 J
2.5 | RAD Sequencing Contracting | Admin | 2017-09-01 | 2018-07-31 | bar: Q4 S; Q4 J
2.6 | RAD Sequencing | Data Processing | 2017-10-01 | 2018-11-30 | bar: Q1 O to Q3 M; Q1 O to Q2 J
2.7 | RADseq data QAQC and filtering | Data Processing | 2018-03-01 | 2018-12-31 | bar: Q2 M to Q3 J; Q1 D; Q2 F
2.8 | RAD loci clustering and SNP calling | Data Processing | 2018-05-01 | 2019-01-31 | bar: Q3 M to Q4 J; Q2 J; Q2 M
2.9 | Completion of Eulerian integrations for 2014-2016 | Data Processing | 2017-06-01 | 2018-06-30 | bar: Q3 J to Q3 J
Milestone 3: Data Interpretation | bar: Q3 J to Q3 M
3.1 | Analyses of spatial population genetic structuring | Data Analysis | 2018-07-01 | 2019-02-28 | bar: Q4 J to Q4 S; Q2 F to Q2 M
3.2 | Analyses of genetic connectivity rate and directionality | Data Analysis | 2018-09-01 | 2019-03-31 | bar: Q4 S to Q1 N; Q2 M to Q3 A
3.3 | Integration of population genetic and modeling data | Modeling | 2018-05-01 | 2019-05-31 | bar: Q3 M to Q3 M
3.4 | Larval Dispersal modeling | Modeling | 2018-01-01 | 2018-12-31 | bar: Q2 J to Q1 D
Milestone 4: Publications | bar: Q3 J to Q3 M
4.1 | Cruise Reports | Publication | 2017-09-01 | 2018-07-31 | bar: Q4 S; Q1 D to Q2 F; Q4 J to Q4 A
4.2 | Dissemination of cruise metadata | Data Management | 2017-09-01 | 2018-08-31 | bar: Q4 S to Q2 M
4.3 | Completion of peer-reviewed publications | Publication | 2019-01-01 | 2019-05-31 | bar: Q2 J to Q3 M
Milestone 5: Outreach | bar: Q3 J to Q3 M
5.1 | Reports to managers | Presentations | 2017-11-01 | 2019-05-31 | bar: Q1 N; Q3 M; Q1 N; Q3 M
5.2 | Scientific Meeting | Presentations | 2019-02-01 | 2019-02-28 | bar: Q2 F
5.3 | End of Project workshop | Workshop | 2019-05-01 | 2019-05-31 | bar: Q3 M
Milestone 6: Reporting | bar: Q3 J to Q3 J
6.1 | Progress reports | Data Management | 2017-11-01 | 2019-05-31 | bar: Q1 N; Q3 M; Q1 N; Q3 M
6.2 | Final Report | Data Management | 2019-01-01 | 2019-05-31 | bar: Q2 J to Q3 M
6.3 | Archive annotated video frames at DSCRTP w/in 6 months after cruise | Data Management | 2018-01-01 | 2018-12-31 | bar: Q2 J; Q3 A; Q1 D
6.4 | Archive coral specimens at NOAA/Harvey Mudd/Smithsonian within 1 yr from collection | Data Management | 2018-07-01 | 2019-06-30 | bar: Q4 J; Q1 O; Q3 J
6.5 | Archive CTD data at NCEI within 1 year from collection | Data Management | 2018-07-01 | 2019-06-30 | bar: Q4 J; Q1 O; Q3 J
6.6 | Archive video at NCEI at end of project | Data Management | 2019-01-01 | 2019-05-31 | bar: Q2 J to Q3 M
6.7 | Archive genetic data at NCBI/Dryad at time of publication | Data Management | 2019-05-01 | 2020-05-31 | bar: Q3 M to Q3 J
6.8 | Archive model output at NCEI at time of publication | Data Management | 2019-05-01 | 2020-05-31 | bar: Q3 M to Q3 J
Meetings | bar: Q3 J to Q3 M
7.1 | Mid-Project PI meeting | Meetings | 2018-04-01 | 2018-04-30 | bar: Q3 A
7.2 | Annual meeting with technical monitors | Meetings | 2018-04-01 | 2018-11-30 | bar: Q3 A; Q1 N
7.3 | Conference calls with technical monitors | Meetings | 2017-06-01 | 2019-05-31 | bar: Q3 J to Q4 J; Q4 S; Q1 N; Q2 J; Q2 M; Q3 M; Q4 J; Q4 S; Q1 N; Q2 J; Q2 M to Q3 M

## Example 2 (planning project)
This Gantt chart is based on an example project focused on reducing the scientific uncertainities around a state agency decision to set nutrient reduction targets and where to place continuous nutrient monitoring stations.
| Task | Task Category | Task Start Date | Task Completion Date | 2021 | 2022
[5 empty] | Q4 | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[5 empty] | S | O | N | D | J | F | M | A | M | J | J | A
Milestone 1: Scoping Activities* | bar: Q4 S to Q4 A
1.1 | Design survey to query nutrient management community on current practices | Meeting Preparation | 2021-09-01 | 2021-09-30 | bar: Q4 S
1.2 | Conduct nutrient management practices survey | Meeting Preparation | 2021-10-01 | 2021-10-31 | bar: Q1 O
1.3 | Design first scoping workshop (virtual) with facilitator | Meeting Preparation | 2021-10-01 | 2021-10-31 | bar: Q1 O
1.4 | Generate initial project scope based on nutrient managment reduction decision and identified uncertainties | Writing | 2021-11-01 | 2021-12-31 | bar: Q1 N to Q1 D
1.5 | Gather feedback on project scope from project team | Data Collection | 2021-12-01 | 2021-12-31 | bar: Q1 D
1.6 | Revise project scope to include feedback and finalize scope | Writing | 2022-01-01 | 2022-01-31 | bar: Q2 J
Milestone 2: Data Collection | bar: Q4 S to Q4 A
2.1 | Nutrient reduction options literature review | Data Collection | 2021-09-01 | 2022-02-28 | bar: Q4 S to Q2 F
2.2 | Review of current nutrient reduction Decision Support Tools | Data Collection | 2021-09-01 | 2022-02-28 | bar: Q4 S to Q2 F
2.3 | Individual watershed characterizations | Data Collection | 2021-09-01 | 2021-01-31 | bar: Q4 S to Q2 J
2.4 | Design nutrient reduction targets and goals survey to query nutrient management community | Data Analysis | 2022-01-01 | 2022-01-31 | bar: Q2 J
2.5 | Conduct nutrient targets and goals survey | Data Collection | 2022-02-01 | 2022-02-28 | bar: Q2 F
2.6 | Design continuous monitoring station location prioritization excercise | Data Analysis | 2022-02-01 | 2021-03-31 | bar: Q2 F to Q2 M
2.6 | Synthesis of literature review and survey results | Data Processing | 2022-02-01 | 2021-03-31 | bar: Q2 F to Q2 M
Milestone 3: Research and Development Plan and Application Plan | bar: Q4 S to Q4 A
3.1 | Draft Research and Development (R&D) Plan | Writing | 2022-04-01 | 2022-05-31 | bar: Q3 A to Q3 M
3.2 | Draft Application Plan | Writing | 2022-04-01 | 2022-05-31 | bar: Q3 A to Q3 M
3.3 | Gather feedback from project team and others on R&D and Application plans | Data Collection | 2022-06-01 | 2022-06-30 | bar: Q3 J
3.4 | Revise R&D Plan and Application Plan | Writing | 2022-07-01 | 2022-07-31 | bar: Q4 J
3.5 | Finalize R&D Plan and Application Plan | Writing | 2022-08-01 | 2022-08-31 | bar: Q4 A
Milestone 4: Meetings and Workshops | bar: Q4 S to Q4 A
4.1 | Initial project meeting | Meetings | 2021-09-01 | 2021-09-30 | bar: Q4 S
4.2 | First scoping workshop (virtual) | Workshop | 2021-11-01 | 2021-11-30 | bar: Q1 N
4.3 | Final scoping meeting - review data synthesis and execute nutrient monitoring station prioritization excercize (virtual) | meetings | 2022-02-01 | 2022-03-01 | bar: Q2 F
4.4 | Meet for drafting R&D Plan and Application Plan | meetings | 2022-03-01 | 2022-04-01 | bar: Q2 M
4.5 | Meeting for final review and updates to R&D Plan and Application Plan (virtual) | meetings | 2022-07-01 | 2022-08-01 | bar: Q4 J
Milestone 5: Reporting | bar: Q4 S to Q4 A
5.1 | Progress reports | Reporting | 2021-02-01 | 2022-08-31 | bar: Q2 F; Q4 A
5.2 | Science Program check ins (60 min web meeting) | Reporting | 2021-12-01 | 2022-06-30 | bar: Q1 D; Q3 A; Q3 J
5.3 | Prepare final report** | Reporting/ Data Management | 2022-08-01 | 2022-08-31 | bar: Q4 A
* These activities should build upon the initial scoping activities described in your proposal
** Final report is due 120 days after the end of the period of performance